## ProjectReport
Field Name | Value
project_name | Bhopal Metro Rail Phase II Depot & Viaduct
state | Madhya Pradesh
district | Bhopal
project_type | URBAN
land_area | 38.5
affected_families | 310
current_stage | Possession
next_stage | Acquisition Completion
snapshot_date | 2026-07-01
latitude | 23.2599
longitude | 77.4126
approvals_required | 12
approvals_completed | 12
approval_process_start_date | 2024-09-15
approval_expected_completion_date | 2026-01-31
oldest_pending_approval_days | 0
legal_cases_total | 5
legal_cases_resolved | 5
disputed_land_area | 0
oldest_pending_case_days | 0
compensation_total_amount | 52000000
compensation_paid_amount | 51200000
beneficiaries_eligible | 305
beneficiaries_compensated | 301
compensation_expected_completion_date | 2026-06-30
documents_required | 310
documents_submitted | 310
documents_verified | 310
notifications_required | 4
notifications_issued | 4
parcels_total | 280
parcels_disputed | 0
ownership_claims_total | 282
ownership_conflicts_pending | 0
ownership_conflicts_resolved | 14
rr_families_required | 75
rr_families_completed | 73
land_required_for_possession | 38.5
land_acquired_for_possession | 36.5
possession_status | SUBSTANTIAL_POSSESSION
stakeholder_requests_raised | 14
stakeholder_responses_received | 14
average_response_time_days | 7.1
departments_involved | 4
coordination_requests_raised | 12
coordination_requests_resolved | 12